## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
As a guest customer, I want to place, pay for, and track orders without creating an account, so that I can quickly order food with minimal friction. | 21 |  | 23 | 23 | 0 | 0 | 6 | 0 | 0 | To Do
Core customer ordering functionality |  | Jamal | 10 | 10 | 0 | 0 | 6 | 0 | 0 |  | 1
Menu System |  | Jamal | 8 | 8 | 0 | 0 | 0 | 0 | 0 |  | 1
Payment System |  | Jamal | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 1
As a restaurant manager, I want to fully manage menu items and their properties, so that customers see accurate, up-to-date menu information. | 13 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | To Do
/menu_items/* Endpoints |  | Jamal | 4 | 4 | 0 | 0 | 0 | 0 | 0 |  | 1
MenuItems Model |  | Jamal | 5 | 5 | 0 | 0 | 0 | 0 | 0 |  | 1
MenuService |  | Jamal | 7 | 7 | 0 | 0 | 0 | 0 | 0 |  | 1
As a kitchen manager, I want to track all ingredients and resources, so that I can prevent stockouts and optimize ordering. | 21 |  | 35 | 0 | 35 | 0 | 0 | 0 | 0 | To Do
/resources/* Endpoints |  | Jamal | 8 | 0 | 8 | 0 | 0 | 0 | 0 |  | 1
/menu_item_ingredients/* Endpoints |  | Jamal | 8 | 0 | 8 | 0 | 0 | 0 | 0 |  | 1
Resource Model |  | Jamal | 6 | 0 | 6 | 0 | 0 | 0 | 0 |  | 1
MenuItemIngredient Model |  | Jamal | 4 | 0 | 4 | 0 | 0 | 0 | 0 |  | 1
InventoryService |  | Jamal | 9 | 0 | 9 | 0 | 0 | 0 | 0 |  | 1
As a restaurant staff member, I want to manage orders from placement to completion, so that customers receive accurate orders promptly. | 17 |  | 17 | 0 | 17 | 0 | 0 | 0 | 0 | To Do
/orders/* Endpoints |  | Jamal | 4 | 0 | 4 | 0 | 0 | 0 | 0 |  | 1
Order model |  | Jamal | 6 | 0 | 6 | 0 | 0 | 0 | 0 |  | 1
OrderService |  | Jamal | 7 | 0 | 7 | 0 | 0 | 0 | 0 |  | 1
As a kitchen staff member, I want to see detailed breakdown of each order, so that I can prepare items accurately. | 8 |  | 12 | 0 | 0 | 12 | 0 | 0 | 0 | To Do
/orderdetails/* Endpoints |  | Jamal | 4 | 0 | 0 | 4 | 0 | 0 | 0 |  | 1
OrderDetail Model with MenuItem relationships |  | Jamal | 8 | 0 | 0 | 8 | 0 | 0 | 0 |  | 1
As a customer and staff member, I want to process payments securely and efficiently, so that transactions are completed safely. | 13 |  | 17 | 0 | 0 | 17 | 0 | 0 | 0 | To Do
/payments/* Endpoints |  | Jamal | 4 | 0 | 0 | 4 | 0 | 0 | 0 |  | 1
Payment Model |  | Jamal | 6 | 0 | 0 | 6 | 0 | 0 | 0 |  | 1
PaymentService |  | Jamal | 7 | 0 | 0 | 7 | 0 | 0 | 0 |  | 1
As a marketing manager, I want to create and manage promotional campaigns, so that I can drive sales and customer loyalty. | 8 |  | 6 | 0 | 0 | 0 | 6 | 0 | 0 | To Do
/promotions/* Endpoints |  | Jamal | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | 1
Promotion Model |  | Jamal | 2 | 0 | 0 | 0 | 2 | 0 | 0 |  | 1
As a customer, I want to leave reviews and ratings for menu items, so that other customers can make informed choices. | 8 |  | 9 | 0 | 0 | 0 | 9 | 0 | 0 | To Do
/reviews/* Endpoints |  | Jamal | 4 | 0 | 0 | 0 | 4 | 0 | 0 |  | 1
Reviews Model with MenuItem relationships |  | Jamal | 5 | 0 | 0 | 0 | 5 | 0 | 0 |  | 1
As a restaurant manager, I want to access comprehensive business analytics, so that I can make data-driven decisions. | 21 |  | 17 | 0 | 0 | 0 | 0 | 17 | 0 | To Do
/staff_actions/analytics/* Endpoints |  | Jamal | 4 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
/staff_actions/revenue/* Endpoints |  | Jamal | 4 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
AnalyticsService |  | Jamal | 9 | 0 | 0 | 0 | 0 | 9 | 0 |  | 1
As a restaurant manager, I want to manage all staff operations efficiently, so that the restaurant runs smoothly. | 13 |  | 23 | 0 | 0 | 0 | 0 | 23 | 0 | To Do
/staff_actions/* Endpoints |  | Jamal | 4 | 0 | 0 | 0 | 0 | 4 | 0 |  | 1
staff_services |  | Jamal | 7 | 0 | 0 | 0 | 0 | 7 | 0 |  | 1
InventoryService |  | Jamal | 6 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
OrderService |  | Jamal | 6 | 0 | 0 | 0 | 0 | 6 | 0 |  | 1
As a system administrator, I want to manage the entire system infrastructure, so that the restaurant system operates reliably. | 8 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | To Do
/administrator_actions/* Endpoints |  | Jamal | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  | 1
TOTAL |  |  | 176 | 39 | 52 | 29 | 21 | 61 | 1 |  | 14